## Netwrok Diagram
Activity | Predecessors | Duration |  | 5 |  | 7 |  | 8 |  | 7 |  | 3 |  | 2
Requirement Gathering and Analysis |  | 5 | Requirements |  | Design |  | Front-End |  | Integration |  | Deploymnet |  | Project Closure
Design | Requurement gathering | 7
Front End Development | Design | 8
Back End Development | Design | 10
Integration | Front-End and Back-End Development | 7 | [5 empty] | 10
Deployment | Integration | 3 |  |  |  |  | Back-End
Project Closure | Deployment | 2