## Calculate TCPI
Activity: EVM Assessing Performance
Complete the calculations in steps 2 to 6 using the space provided.
Step 2: Identify the TCPI formula best suited to the scenario.
Step 3: Determine the Budget at Completion (BAC).
Formula
Calculation
BAC (in hours)
Step 4: Determine the Actual Cost (AC) after 3 weeks.
Formula
Calculation
AC (in hours)
Step 5: If the BAC is 70 hours, determine the Earned Value (EV) after 3 weeks.
Formula
Calculation
EV (in hours)
Step 6: Calculate the To-Complete Performance Index and interpret the result.
Formula
Calculation
TCPI
Threshold comparison (TCPI < 1, TCPI = 1, TCPI > 1)