## Calculate performance metrics
Given information
Baseline schedule (in months) | 12
Status date (in months) | 6
Planned Value (PV) | 500000
Earned Value (EV) | 450000
Actual Cost (AC) | 480000
Step 1: Calculate the Cost Variance (CV) from the given scenario by applying the CV formula. What does this indicate?
Formula
Calculation
Threshold comparison |  | (CV = 0, CV < 0, CV > 0)
Interpretation: What does the CV indicate about cost performance so far?
Step 2: Calculate the Schedule Variance (SV) from the given scenario by applying the SV formula. What does this indicate?
Formula
Calculation
Threshold comparison |  | (SV = 0, SV < 0, or SV > 0)
Interpretation: What does the SV indicate about schedule performance so far?
Step 3: Calculate the Cost Performance Index (CPI). What does this indicate?
Formula
Calculation
Threshold comparison |  | (CPI = 1, CPI < 1, or CPI > 1)
Interpretation: What does the CPI indicate about the cost efficiency of the project so far?
Step 4: Calculate the Schedule Performance Index (SPI). What does the SPI indicate?
Formula
Calculation
Threshold comparison |  | (SPI = 1, SPI < 1, or SPI > 1)
Interpretation: What does the CPI indicate about the schedule efficiency of the project so far?