## Activities
Activity | Description | Optimistic Time (O) | Most likely Time (M) | Pessimistic (P) | Expected duration | Standard deviation
A | Script Writing | 15 | 25 | 40
B | Casting | 10 | 20 | 30
C | Location Scouting | 5 | 10 | 20
D | Filming | 50 | 70 | 100
E | Editing | 20 | 30 | 45
F | Promotion | 10 | 15 | 25

## Network diagram
Network diagram based on the most likley estimates
| 25 |  | 20 |  | 70 |  | 30 |  | 15
Script writing |  | Casting |  | Filming |  | Eiting |  | Promotion
10
Location scout